## Defects
Defect # | Status | Raised By | Tested on Version | TestCase Id | Steps to Reproduce | Expected Results | Actual Results | Priority | Severity | commint
1 | Closed | Nermeen | V1 | NC004 | Open the url https://demo.guru99.com/V1 Choose New customer write in name feild Ne meen Write in all feilds valid data Select submit | An error message"Empty characters are not allowed" | An error message"Numbers are not allowed" | High | low | Fixed in V2
2 | Closed | Nermeen | V1 | NC005 | Open the url https://demo.guru99.com/V1 Choose New customer Write in all feilds valid data Select submit | Message shows that customer has created sussccefully | 1) could not find user id field 2) It moved to another page shows an error "Connection failed: Access denied for user 'root'@'localhost' (using password: NO)" | High | Critical | Fixed in V2
3 | closed | Nermeen | V1 | NC006 | Open the url https://demo.guru99.com/V1 Choose New customer Write in Address field "Sh obra,RoudElfrg,Cairo" Write in all feilds valid data Select submit | An error message "Address can not Contain an empty character"must shown | It moved to another page shows an error "Connection failed: Access denied for user 'root'@'localhost' (using password: NO)" | High | Critical | Fixed in V2
4 | Closed | Nermeen | V1 | NC007 | Open the url https://demo.guru99.com/V1 Choose New customer Write in Address field "Sh obra,RoudElfrg,Cairo" Write in all feilds valid data Select submit | An error message "Address can not Contain an empty character"must shown | It moved to another page shows an error "Connection failed: Access denied for user 'root'@'localhost' (using password: NO)" | High | Critical | Fixed in V2
5 | Open | Nermeen | V1 | NC008 | Open the url https://demo.guru99.com/V1 Choose New customer Write in Address field "Shobra@, St.Road Elfrag" Write in all feilds valid data Select submit | An error message "Special Characters are not allowed"must shown | An alart shows"Please fill all fields" | high | low | Fixed in V4
6 | closed | Nermeen | V1 | NC015 | Open the url https://demo.guru99.com/V1 Choose New customer write in City feild C airo Write in all feilds valid data Select submit | An error message"Empty characters are not allowed" | An error message"Numbers are not allowed" | High | low | Fixed in V2
7 | Open | Nermeen | V1 | NC028 | Open the url https://demo.guru99.com/V1 Choose New customer write in emai feild Tes t8@gmail.com Write in all feilds valid data Select submit | An error message "Inavlid email"must shown | An alart shows"Please fill all fields" | High | low
8 | closed | Nermeen | V1 | NC029 | Open the url https://demo.guru99.com/V1 Choose New customer write in email feild Test8@gmail.com Write in all feilds valid data Select submit | An error message "This email address is already exists "must shown | It moved to another page shows an error "Connection failed: Access denied for user 'root'@'localhost' (using password: NO)" | High | Critical | Fixed in V2
11 | closed | Nermeen | V1 | EC002 | Enter customer id with Special characters and number Select Submit | An error message "Special characers are not allowed" must shown | can not be done due to connection error | High | Critical | Fixed in V2
12 | closed | Nermeen | V1 | EC003 | Enter customer id with characters and numbers Select Submit | An error message "Characters are not allowed" must shown | Can not be done due to connection error | High | Critical | Fixed in V2
13 | closed | Nermeen | V1 | EC004 | Enter customer include space character | An error message "Invalid customer id" must shown | Can not be done due to connection error | High | Critical | Fixed in V2
14 | closed | Nermeen | V1 | EC005 | Edit on customer with an address begins with empty character | An error message "First character can not have space"must shown | Can not be done due to connection error | High | Critical | Fixed in V2
15 | closed | Nermeen | V1 | EC006 | Edit on customer with empty address | An error message "Address Field must not be blank"must shown | Can not be done due to connection error | High | Critical | Fixed in V2
16 | closed | Nermeen | V1 | EC007 | Edit on a customer which is not associated with the manager | An error message "You are not authorize to edit this customer!!"must shown | Can not be done due to connection error | High | Critical | Fixed in V2
17 | closed | Nermeen | V1 | EC008 | Edit on customer with an address including special character | An error message "Special characters are not allowed "must shown | Can not be done due to connection error | High | Critical | Fixed in V2
18 | closed | Nermeen | V1 | EC009 | Edit on customer with empty city | An error message "City can not be empty"must shown | Can not be done due to connection error | High | Critical | Fixed in V2
19 | closed | Nermeen | V1 | EC010 | Edit Customer with city including special character | An error message "special characters are not allowed"must shown | Can not be done due to connection error | High | Critical | Fixed in V2
20 | closed | Nermeen | V1 | EC011 | Edit on customer with city including numbers | An error message "Numbers are not allowed"must shown | Can not be done due to connection error | High | Critical | Fixed in V2
21 | closed | Nermeen | V1 | EC012 | Edit on customer with empty state | An error message "State can not be empty"must shown | Can not be done due to connection error | High | Critical | Fixed in V2
22 | closed | Nermeen | V1 | EC013 | Edit on customer with state including special character | An error message "Special characters are not allowed"must shown | Can not be done due to connection error | High | Critical | Fixed in V2
23 | closed | Nermeen | V1 | EC014 | Edit on customer with state including numbers | An error message "Numbers are not allowed"must shown | Can not be done due to connection error | High | Critical | Fixed in V2
24 | closed | Nermeen | V1 | EC015 | Edit on customer with state begins with empty character | An error message "State can not begin with empty character"must shown | Can not be done due to connection error | High | Critical | Fixed in V2
25 | closed | Nermeen | V1 | EC016 | Edit on customer with PIN code including characters | An error message "Characters are not allowed"must shown | Can not be done due to connection error | High | Critical | Fixed in V2
26 | closed | Nermeen | V1 | EC017 | Edit on customer with empty PIN code | An error message "PIN code can not be empty"must shown | Can not be done due to connection error | High | Critical | Fixed in V2
27 | closed | Nermeen | V1 | EC018 | Edit on customer with PIN code its length less than 6 | An error message "PIN code must have 6 digits "must shown | Can not be done due to connection error | High | Critical | Fixed in V2
28 | closed | Nermeen | V1 | EC019 | Edit on customer with PIN code including special characters | An error message "Special characters are not allowed"must shown | Can not be done due to connection error | High | Critical | Fixed in V2
29 | closed | Nermeen | V1 | EC020 | Edit on customer with PIN code its length more than 6 | An error message "PIN code must have 6 digits "must shown | Can not be done due to connection error | High | Critical | Fixed in V2
30 | closed | Nermeen | V1 | EC021 | Edit on customer with PIN code starts with empty character | An error message "PIN code can not begin with empty character "must shown | Can not be done due to connection error | High | Critical | Fixed in V2
31 | closed | Nermeen | v1 | EC022 | Edit on customer with empty telephone number | An error message "Telephone number can not be empty "must shown | Can not be done due to connection error | High | Critical | Fixed in V2
32 | closed | Nermeen | v1 | EC023 | Edit on customer with telephone number including characters | An error message "characters are not allowed"must shown | Can not be done due to connection error | High | Critical | Fixed in V2
33 | closed | Nermeen | v1 | EC024 | Edit on customer with telephone number including special characters | An error message "Special characters are not allowed"must shown | Can not be done due to connection error | High | Critical | Fixed in V2
34 | closed | Nermeen | V1 | EC025 | Edit on customer with telephone number begins with empty character | An error message "Telephone number can not begin with epty space "must shown | Can not be done due to connection error | High | Critical | Fixed in V2
35 | closed | Nermeen | V1 | EC026 | Edit on customer with telephone number begins with empty character | An error message "Telephone number can not begin with epty space "must shown | Can not be done due to connection error | High | Critical | Fixed in V2
36 | closed | Nermeen | V1 | EC027 | Edit on customer with empty email | An error message "Email can not be empty"must shown | Can not be done due to connection error | High | Critical | Fixed in V2
37 |  | Nermeen | V1 | EC028 | Edit on customer with invalid email | An error message "Inavlid email"must shown | Can not be done due to connection error | High | Critical
38 | closed | Nermeen | V1 | EC029 | Edit on customer with email begins with empty character | An error message "Inavlid email"must shown | Can not be done due to connection error | High | Critical | Fixed in V2
39 | closed | Nermeen | V1 | DC001 | Enter an empty customer id Select submit | An error message "Customer id is required" must shown | Can not be done due to connection error | High | Critical | Fixed in V2
40 | closed | Nermeen | V1 | DC002 | Enter a customer id including special characters Select Submit | An error message "Invalid Customer Id" must shown | Can not be done due to connection error | High | Critical | Fixed in V2
41 | closed | Nermeen | V1 | DC003 | Enter customer id including characters Select Sumit | An error message "Invalid Customer Id" must shown | Can not be done due to connection error | High | Critical | Fixed in V2
42 | closed | Nermeen | V1 | DC004 | Enter customer id begins with space Select Submit | An error message "Invalid Customer Id" must shown | Can not be done due to connection error | High | Critical | Fixed in V2
43 | Open | Nermeen | V1 | DC005 | Enter valid customer Id Select Submit | A message shows that he customer is deleted successfully | Can not be done due to connection error | High | Critical
44 | closed | Nermeen | V1 | DC006 | Delete a customer which is not associated with the manager Select Submit | An error message "It is not allowed to access this account"must shown | Can not be done due to connection error | High | Critical | Fixed in V2
45 | closed | Nermeen | V1 | NA001 | Entner an empty customer id Select Submit | An error message "Customer id is required" must shown | Moved to another page shows"Connection failed: Access denied for user 'root'@'localhost' (using password: NO)" | High | Critical | Fixed in V2
46 | closed | Nermeen | V1 | NA002 | Enter a customer id including special characters Select Submit | An error message "Special characters are not allowed" must shown | No error message is shown | High | Medium | Fixed in V2
47 | closed | Nermeen | V1 | NA003 | Enter a customer id including characters Select Submit | An error message "Charaters are not allowed" must shown | No error message is shown | High | Medium | Fixed in V2
48 | closed | Nermeen | V1 | NA004 | Enter a customer id includes a space character Select Submit | An error message "Invalid customer id" must shown | No error message is shown | High | Medium | Fixed in V2
49 | closed | Nermeen | V1 | NA005 | Enter a valid customer Id Select submit | A message "New acccount is added successfully" must shown | Moved to another page shows"Connection failed: Access denied for user 'root'@'localhost' (using password: NO)" | High | Critical | Fixed in V2
50 | closed | Nermeen | V1 | NA006 | Enter an initial value less than 500 | An error message "Initail value must be 500 or more" must shown | Moved to another page shows"Connection failed: Access denied for user 'root'@'localhost' (using password: NO)" | High | Critical | Fixed in V2
51 | closed | Nermeen | V1 | NA007 | Enter a customer id that is not associated with manger | An error message "It is not allowed to access this account"must shown | Can not be done due to connection error | High | Critical | Fixed in V2
52 | closed | Nermeen | V1 | NA008 | Enter an initial value equal 500 | A message "New account added successfully" must shown | Moved to another page shows"Connection failed: Access denied for user 'root'@'localhost' (using password: NO)" | High | Critical | Fixed in V2
53 | Open | Nermeen | V1 | EA004 | Enter a valid account no | A messgae "updated successfully"must show | Can not be done due to connection error | High | Critical
54 | Open | Nermeen | V1 | EA005 | Enter a customer id not associated with manger | An error message "It is not allowed to access this account"must shown | Can not be done due to connection error | High | Critical
55 | Open | Nermeen | V1 | DA004 | Enter a valid account no Select Submit | A message "Deleted successfully" must shown | Can not be done due to connection error | High | Critical
56 | Open | Nermeen | V1 | CS004 | View transactions with valid account no | A message "Deleted successfully" must shown | Moved to another page shows"Connection failed: Access denied for user 'root'@'localhost' (using password: NO)" | High | Critical
57 | Open | Nermeen | V1 | CS005 | View transactions with from date greater than to date | An error message "Enter valid Date" must shown | shows"Connection failed: Access denied for user 'root'@'localhost' (using password: NO)" | High | Critical
58 | Open | Nermeen | V1 | CS006 | View transactions with To date greater than from date | "Transactions details will be dispalyed" | shows"Connection failed: Access denied for user 'root'@'localhost' (using password: NO)" | High | Critical
59 | Open | Nermeen | V2 | CS007 | Enter values in all fields except amount lower limitt field | An error message "Amount Lower Limit is required " must shown | No error message is shown | High | High
60 | OPen | Nermeen | V3 | CS008 | Enter values in all fields except From Date field | An error message "From Date is required " must shown | No error message is shown | High | High
61 | OPen | Nermeen | V4 | CS009 | Enter values in all fields except To Date field | An error message "To Date is required " must shown | No error message is shown | High | High
62 | OPen | Nermeen | V5 | CS010 | Enter values in all fields except Number Of Transaction field | An error message "Enter Number Of Transaction is required " must shown | No error message is shown | High | High
63 | Open | Nermeen | V1 | MS004 | View transactions with valid account no | "Transactions details will be dispalyed" | shows"Connection failed: Access denied for user 'root'@'localhost' (using password: NO)" | High | Critical
64 | Open | Nermeen | V1 | MS005 | View transactions with invalid account no | An error message "Invalid account no" must shown | shows"Connection failed: Access denied for user 'root'@'localhost' (using password: NO)" | High | Critical
65 | Open | Nermeen | V1 | MS006 | View transactions with account no not associated with manager | An error message "It is not allowed to access the transactions of this acount" must shown | Can not be done due to connection error | High | Critical
66 | closed | Nermeen | V1 | IP1 | Check new Customer is created | Message Should be display "Customer added successfully !!" | No message is shown It moved to another page shows an error "Connection failed: Access denied for user 'root'@'localhost' (using password: NO)" | High | Critical | Fixed in V2
67 | closed | Nermeen | V1 | IP2 | Verify Customer is not added twice | Message Should be displayed"Email address already exist" | No message is shown It moved to another page shows an error "Connection failed: Access denied for user 'root'@'localhost' (using password: NO)" | High | Critical | Fixed in V2
68 | Open | Nermeen | V1 | IP3 | Check Customer can be edited | Message Should be displayed" customer records updated successfully!!" | Can not be done due to connection error | High | Critical
69 | Open | Nermeen | V1 | IP4 | Verify Customer should not be edited for same email id and user id | Message Should be display" customer records updated successfully!!" | Can not be done due to connection error | High | Critical
70 | closed | Nermeen | V1 | IP5 | Verify Non existing Customer is not Edited | Message Should be display" You are not authorise to edit this customer!!" | Can not be done due to connection error | High | Critical | Fixed in V2
71 | closed | Nermeen | V1 | IP6 | Check New account is added | Message Should be display " account generated successfully" | Can not be done due to connection error | High | Critical | Fixed in V2
72 | closed | Nermeen | V1 | IP7 | Verify that New Account is not added when same account id already exist | Message Should be display " account generated successfully" | Can not be done due to connection error | High | Critical | Fixed in V2
73 | closed | Nermeen | V1 | IP8 | Check Ministatement is generated | Display Generated ministatement | Can not be done due to connection error | High | Critical
74 | Open | Nermeen | V1 | IP9 | Check Account is edit | Message Should be display " account detail successfully updated" | Can not be done due to connection error | High | Critical
75 | Open | Nermeen | V1 | IP10 | Check Customized Statement is generate | Display Generated ministatement | Can not be done due to connection error | High | Critical
76 | Open | Nermeen | V1 | IP11 | Verify Account is delete | Message Should be display"Account deleted Successfully" | Can not be done due to connection error | High | Critical
77 | Open | Nermeen | V1 | IP12 | Verify Non Existing Account is not edited | Message Should be display"Account does not exist " | Can not be done due to connection error | High | Critical
78 | Open | Nermeen | V1 | IP13 | Verify Non Existing Account is not be deleted | Message Should be display"Account does not exist " | Can not be done due to connection error | High | Critical
79 | Open | Nermeen | V1 | IP14 | Check Ministatement is not generated | Message Should be display - "Account does not exist" | Can not be done due to connection error | High | Critical
80 | Open | Nermeen | V1 | IP15 | Verify Customer is Deleted | Message Should be display"Customer could not be deleted " | Can not be done due to connection error | High | Critical
81 | Open | Nermeen | V1 | IP16 | Check Customized Statement is not generated | Message Should be display"You are not authorise to delete this account " | Can not be done due to connection error | High | Critical
82 | Open | Nermeen | V1 | IP17 | Verify Ministatement is generated | Displayed Generated ministatement | Can not be done due to connection error | High | Critical
83 | Open | Nermeen | V1 | IP18 | Check Customized Statement is generated | Display Generated Customized statement | Can not be done due to connection error | High | Critical
84 | Open | Nermeen | V1 | Test home button | click on home button | redirect to manager home | moved to page shows "404 Not Found error was encountered while trying to use an ErrorDocument to handle the request." | High | Critical
85 | Open | Nermeen | V2 | EC032 | veritfy that the change is submitted successfully | A message "Edit successfully" is shown | an error message"No Changes made to Customer record" | High | Critical
86 | Open | Nermeen | V2 | EA006 | Try to edit customer id | An error message "customer id is disabled" | This page isn’t working | High | Critical
87 | Open | Nermeen | V2 | EA007 | Try to edit on Balane field | An error message "balance is disabled" | This page isn’t working | High | Critical
88 | Open | Nermeen | V2 | BE005 | Enter a valid Account No | "Balance details will be dispalyed" | an error message"This page isn’t working"is shown | High | Critical
89 | Open | Nermeen | V2 | BE006 | Enter a valid Account No exist in database | "Balance details will be dispalyed" | an error message"This page isn’t working"is shown | High | Critical
90 | Open | Nermeen | V2 | BE007 | Enter a invalid Account No exist in database | An error message is shown"you dont have access on this account" | an error message"This page isn’t working"is shown | High | Critical